## CHECKLIST
______________________________ Tournament Task List
Secretary - ___________________ Venue Booked & Time - _______________ |  | Date | TS - Tournament Secretary
|  | / / | R - Referee
DONE | 12+ Weeks BEFORE Tournament | Action by; | NOTES - Date
| New organiser: Set-up paypal account | TS
| New organiser: Install Tournament Planner (TP) on your computer / Register TP with licence | TS
| Book venue | TS
| Online circuit tournament sanction application | TS
| Open/download tournament (see 'Approved Tournament Sacntion - Next Steps' / restore if back-up) | TS
| Add BE standard regulations (make optional amends), payment info, message box info | TS
| Check regulations for accuracy | R
| Publish tournament - check online entry is open | TS
| Email the Umpire Secretary if using to request booking | TS
| Email players/contacts advertising the tournament | TS
DONE | 4-5 Weeks BEFORE Tournament | Action By; | NOTES - Date
| Email the Umpire Secretary if using to confirm booking | TS
| Email the player database advertising the tournament if needed | TS
| Recruit all key helpers required | TS | Match Control -
| Initial capacity assessment (ROUGH SCHEDULE) & entry extended if required | TS & R | Court Manager(s) -
| If oversubscribed - Do not accept new entries / Do not partner players / Add players to the reserve list | TS | Welfare/Safeguarding Officer -
| Confirm venue set-up requirements / equipment list (check catering / parking provision) | TS | First Aider -
| Medal / Shuttle Ordered (BE shuttles and medals should arrive the week before the tournament) | TS | Publicity Officer -
DONE | 3 Weeks BEFORE Tournament / Entry Closed | Action By; | NOTES - Date
| Final entry numbers decided (SCHEDULE) | TS & R
| Player validation & Ranking imported to TP (Use current closing date for Grading/Ranking timings) | TS
| Player seeding completed (referee to check) & published | TS & R
| Email Umpires if using to confirm arrangements/timings after scheduled | TS
| Agree helpers for the day with a minimum of three per venue 100% of the day | TS
| Check all tournament kit | TS
DONE | 2 Weeks BEFORE Tournament | Action By; | NOTES - Date
| Tournament helpers - Finalise all volunteers & Roles, with a minimum of three 100% of the day | TS
| Draws made | R
| Schedule all events and match times added to TP | TS & R
| Add guide registration times to message box / Publish (do not publish draws until 48 hours before) | TS
| Player information, acceptance, and first match times emailed through TP - 'First Match Times' | TS
DONE | 1 Week BEFORE Tournament | Action By; | NOTES - Date
| Check shuttles + knocks __________+___________ Given / Check medals given _____________ | TS
| Player changes managed - Move players from reserve lists / amend draws & Schedule as required | TS & R
| Inform any players with a new first match time | TS
| Draw published - 48 hours prior to tournament start | TS
| Print match slips | TS
| Print Paperwork (as required) - Photography Registration forms / Safeguarding poster / Codes of conduct / Draws for wall /Player Registration form (can do on TP) / Acceptance Letter copy for desk / Tournament & Venue Guidelines / Player greeting signs / Desk layout & plan | TS
DONE | Tournament Day | Action By; | NOTES - Date
| Take all the kit & set up from 8am - referees desk, PA. waiting benches, spectator seating, signage etc… | TS & Team
| Check the courts / Nets / Posts / Curtain / Lighting | R
| Set up Laptop & TP | TS
| Sign players in on a register sheet (or TP) - sorting out any money owed or to be refunded | Match control
| Welcome players (note that not all players arrive fo the start so important information that all players need to know should ideally be provided to players before the tournament | TS / R
| Manage shedule and allocate matches to court | Match control
| Manage play and support umpires | R / Umpire Manager
| Present event medals at the end of each event on a court next to the desk / gather all players who played in that event / Announcing the winners in reverse order / Ask an important person to hand out the medals | TS / R / VIP
| At the end thank the players, parents, coaches & ALL helpers | TS / R / VIP
DONE | within 5 Days of Tournament | Action By; | NOTES - Date
| Publish the completed tournament on the BE website through TP | TS | Refund fees:
| Update TP with all payments received on the day & pass money & chq's to TC | TS | None - Before entry deadline
| Refund of entry fees (paypal) | TS | None - reserve lists
| Complete Referee report [Players = BS= GS= BD= GD= XD= Matches= Shuttles= | TS | None - doubles partner withdrew
| Thank you email to everyone that helped inc venue staff if applicable | TS | £10 - After deadline/before draw
|  | TS | NO REFUNDS within 48 hours of start